## Gap Phases
ThriveAtHome Gap Build Tracker — G1 to G4 (40 phases)
Update the Status column as the build loop finishes each phase (pick from the dropdown). Source: gaps/ specs in the repo, Sept 30, 2026.
Spec | Phase | Name | What it builds | Migration | Status | Notes
G1 | G1.1 | Call record schema fix | Adds agent, direction and caller columns; fixes the bug where every completed call fails to save | 085 | Not started
G1 | G1.2 | Agent registry | Maps all 12 Retell agents to their env vars so each can be used | — | Not started
G1 | G1.3 | Webhook security | Verifies requests come from Retell; secures tool routes; adds missing call-preferences tool | — | Not started
G1 | G1.4 | Call-ended processing | Saves inbound + outbound calls, crisis detection, AI summaries, mood scores, alerts, family summary | — | Not started
G1 | G1.5 | Aria opt-in + Launch Protocol | Aria calls only for opted-in members; navigator welcome and Day-21 tasks | — | Not started
G1 | G1.6 | Joy + Grace calls | Joy birthday/milestone calls; Grace appointment reminder calls | 085 | Not started
G1 | G1 review | Human review + pull request | Run the spec's human review steps; merge the PR; reply APPROVED | — | Not started
G2 | G2.0 | RLS helpers | Shared access rules for seniors logging in directly and family accounts | 086 | Not started
G2 | G2.1 | Post comments | Comment threads on circle posts with notifications | 086 | Not started
G2 | G2.2 | Report & moderation | Report posts/comments; navigator hide or dismiss | 086 | Not started
G2 | G2.3 | Event proposals + 41a | Members propose events for approval; All-Communities events, external RSVP, attendee names | 086 | Not started
G2 | G2.4 | Circle members tab | Opt-in member list on each circle | — | Not started
G2 | G2.5 | Friends + private messages | Friend requests and messaging, screened for scams | 087 | Not started
G2 | G2.6 | Facilitated introductions | Navigator-arranged warm introductions between members | 087 | Not started
G2 | G2 review | Human review + pull request | Run the spec's human review steps; merge the PR; reply APPROVED | — | Not started
G3 | G3.4 | Fraud flags + detector | Scam detection on calls, messages and gift orders; family sees flags | 089 | Not started
G3 | G3.1 | Family events calendar | Family dates Aria mentions on calls; day-of send buttons | 088 | Not started
G3 | G3.2 | Cards, notes & gifts | Senior sends cards/gifts; family approval over $75 or for gift cards | 088 | Not started
G3 | G3.3 | Family-initiated celebrations | Free / $25 / $75 celebration tiers with family coordination room | 088 | Not started
G3 | G3 review | Human review + pull request | Run the spec's human review steps; merge the PR; reply APPROVED | — | Not started
G4 | G4.1 | HV importer + sync | Import Helpful Village CSV exports; honest sync status | 090 | Not started
G4 | G4.2 | SMS broadcasts | Text option for org broadcasts and family nudges; STOP opt-out | 090 | Not started
G4 | G4.3 | Geocoding & distance | Distance-based volunteer matching and search | 090 | Not started
G4 | G4.4 | Grief circles | Navigator-run facilitated grief support groups | 090 | Not started
G4 | G4.5 | Thrive Device kiosk | Tablet pairing, /device screen, device management | 090 | Not started
G4 | G4.6 | Transport dispatch tiers | Volunteer → Lyft → AV partner ride routing | — | Not started
G4 | G4.7 | Volunteer training | Required training modules and hour badges | 090 | Not started
G4 | G4.8 | Language Line bridge | Interpreter hand-off on Quinn calls | — | Not started
G4 | G4 review | Human review + pull request | Run the spec's human review steps; merge the PR; reply APPROVED | — | Not started
G5 | G5.1 | Medicare: MA data + member help | Populate the clinical fields MA reports read (currently always empty); report hardening; Medicare plan help, HICAP referral, Open Enrollment reminders | 091+ | Not started
G5 | G5.2 | Paid companion payouts | Stripe Connect onboarding and 20% fee for paid companions; Premier $50/month credits | 091+ | Not started
G5 | G5.3 | Geographic chapters | Metro areas, chapter auto-activation at 50 members, same-chapter matching | 091+ | Not started
G5 | G5.4 | Celebrations depth | 7-day birthday arc, milestone-age programmes (70–100), achievements, home-from-hospital welcome | 091+ | Not started
G5 | G5.5 | Life transitions depth | 4 new pathways, 6-week facility-move plan, therapist/chaplain warm introductions | 091+ | Not started
G5 | G5.6 | Interest circles + cultural content | Veterans, LGBTQ+ (private), Widows & Widowers, Professional Identity circles; cultural content feed | 091+ | Not started
G5 | G5.7 | Plan entitlements + SKUs | Navigator hours, family seat limits, 4 missing add-ons | 091+ | Not started
G5 | G5.8 | Family summary text + event rides | Daily call summary text to family; ride booked with event RSVP | — | Not started
G5 | G5.9 | FHIR referrals + compare pages | Hospital discharge referrals via FHIR R4; 4 comparison pages | 091+ | Not started
G5 | G5.10 | Volunteer ecosystem completion | VSO affiliations + VAVS export, corporate tiers, family reciprocity credits | 091+ | Not started
G5 | G5 review | Human review + pull request | Run the spec's human review steps; merge the PR; reply APPROVED | — | Not started
G6 | G6.0 | Community partners | Outbound partner directory, consented referrals, follow-up check-ins | 091+ | Not started
G6 | G6.1 | Home Safety & Earthquake Prep | Modelled on Foster City Village: yearly programme, volunteers with 3–5 homes, training, inspection, itemised proposal (all/some/none), licensed contractor work, free/subsidised/member-pays costs, fridge magnet, Go-Bag, presentation series, grant report | 091+ | Not started
G6 | G6.2 | Home Sharing | Interest form and warm referral to HIP Housing (San Mateo); demand tracking elsewhere | 091+ | Not started
G6 | G6.3 | Encore Careers | Career profile, opportunities board, SCSEP/job-centre referrals, internal paid roles | 091+ | Not started
G6 | G6.4 | Member-in-Need Campaigns | Admin-verified giving campaigns paid to partner org or vendor; legal/Stripe review before launch | 091+ | Not started
G6 | G6 review | Human review + pull request | Run the spec's human review steps; merge the PR; reply APPROVED | — | Not started
Summary
|  | Build phases | 40
|  | Done | 0
|  | In progress | 0
|  | Blocked | 0
|  | % complete | 0%

## Partners
Community partners to confirm before activation (seeded as pending)
Partner | Used by | County | Phone | What they do | Confirmed? (Y/N) | Notes
Hassett Hardware — Handyman Program | G6.1 | San Mateo (Foster City) | Confirm | Licensed contractor partner in Foster City Village's home safety programme
HIP Housing — Home Sharing Program | G6.2 | San Mateo | 650-348-6660 | Screens and matches home providers and seekers; Living Together Agreement; follow-up; home visits for homebound seniors
Rebuilding Together Peninsula — Safe at Home | G6.1 | San Mateo; north Santa Clara | 650-366-6597 | Free safety and health repairs for low-income homeowners
Center for Independence of Individuals with Disabilities | G6.1 | San Mateo | 650-645-1780 | Grab bars, railings, ramps
Felton Institute — SCSEP | G6.3 | San Mateo; Marin | Confirm | Paid part-time community service training for low-income adults 55+
NOVAworks Job Center — San Mateo | G6.3 | San Mateo | Confirm | Job search, training, coaching (1777 Borel Place, Suite 500)
HICAP of San Mateo County | G5.1 | San Mateo | Confirm | Free Medicare counselling
AARP Foundation | G6.3 | National | Confirm | Back to Work 50+ and SCSEP nationally
AmeriCorps Seniors | G6.3 | Local sponsors | Confirm | RSVP, Senior Companion, Foster Grandparent
CoGenerate (formerly Encore.org) | G6.3 | National | Confirm | Encore fellowships, intergenerational roles

## Not Included
Deliberately left out of the gap build
Item | Why | Who / when
Full multilingual UI (Phase 55) | Roadmap puts it last, after M19–M27 | Build later
Business Associate Agreements (Supabase, Twilio, Anthropic, Retell, Checkr) | Legal agreements, not code | You — before real members
API keys in Vercel (12 Retell agent IDs, RETELL_API_KEY, TWILIO_PHONE_NUMBER, ANTHROPIC_API_KEY, SENDGRID_API_KEY) | Credentials, not code | You — needed to test real calls
Stripe live mode | Account setting | You — when ready for real payments
Legal + Stripe review of member-in-need campaigns (G6.4) | Tax and payment-processor rules must be confirmed before real donations | You + counsel
Senior mobile app (React Native), Alexa/Google skills | Vision items with no current build plan | Later roadmap

## Reliability & Limits
How the build loop works — and its limits
Topic | Detail
Testing | After every phase: its checklist, type check (tsc) and lint must all pass before moving on
Getting stuck | After 3 failed fixes on one item it stops as BLOCKED and asks you
SQL | Stops and names the migration file to run in the Supabase SQL Editor; reply DONE
Human checkpoints | At the end of G1 to G6: human review steps + a pull request; reply APPROVED after merging
Nothing reaches main without you | Work happens on gaps/g1…g6 branches; you merge each pull request
Real integrations | Tests use your real Retell, Twilio, Anthropic, SendGrid and Stripe test accounts — calls and texts only to TEST_PHONE_NUMBER, Stripe test mode only
Limit: usage limits (Pro plan) | If it stops, wait for the reset, run claude again and paste: Read gaps/GAP_BUILD_PROMPT.md and follow it exactly.
Alternative: per-phase checks | ./build-gaps.sh pauses after every phase, like your original build.sh